## Sheet1
Task Name | % Complete | Work | Duration | Start | Finish | Predecessors | Resource Initials
SampleImplementationProjectPlanNew | 0% | 2,412 hrs | 492 days | Tue 5/28/13 | Wed 5/6/15
Phase 1 - Assessment | 100% | 0 hrs | 36 days | Mon 8/5/13 | Tue 9/24/13
Assessment | 100% | 0 hrs | 36 days | Mon 8/5/13 | Tue 9/24/13
Phase 2 - Plan | 0% | 0 hrs | 60.5 days | Mon 9/30/13 | Thu 12/26/13
Validate Program Management Office & Controls | 0% | 0 hrs | 18 days | Wed 10/2/13 | Fri 10/25/13
Validate Steering Committee (SC) - representatives of HIM, Revenue Cycle, IT and Finance | 0% | 0 hrs | 5 days | Wed 10/2/13 | Tue 10/8/13 | 2FS+5 days
Create a SC charter including overall objective, standing agenda, and meeting frequency | 0% | 0 hrs | 1 day | Wed 10/9/13 | Wed 10/9/13 | 5
Identify a PMO project manager and validate PMO staffing approach | 0% | 0 hrs | 1 day | Thu 10/10/13 | Thu 10/10/13 | 6
PMO assumes ownership of the overall project roadmap and budget | 0% | 0 hrs | 6 days | Fri 10/11/13 | Fri 10/18/13 | 7
Assign team leaders to each work thread | 0% | 0 hrs | 5 days | Mon 10/21/13 | Fri 10/25/13 | 8
Develop progress status reporting structure between PMO and work thread team leaders | 0% | 0 hrs | 5 days | Mon 10/21/13 | Fri 10/25/13 | 8
Develop progress status reporting structure between PMO and Steering Committee | 0% | 0 hrs | 5 days | Mon 10/21/13 | Fri 10/25/13 | 8
Develop progress reporting structure between Steering Committee and Executive Management | 0% | 0 hrs | 5 days | Mon 10/21/13 | Fri 10/25/13 | 8
Develop a "Risk Register" &"Issues Log" to document initial project risks & assumptions | 0% | 0 hrs | 5 days | Mon 10/21/13 | Fri 10/25/13 | 8
Validate Project Budget, Work Plan & Gain Signoff across teams | 0% | 0 hrs | 49 days | Mon 9/30/13 | Mon 12/9/13
Integrate Education & Training Plan into Implementation Roadmap | 0% | 0 hrs | 5 days | Mon 10/28/13 | Fri 11/1/13 | 9
Validate Work Threads with Team Leaders/Project Owners | 0% | 0 hrs | 15 days | Mon 11/4/13 | Fri 11/22/13 | 15
Validate ICD-10 Remediation Project Budget with Team Leaders/Project Owners | 0% | 0 hrs | 20 days | Mon 9/30/13 | Thu 11/21/13
Signoff on Work Threads Plan from Team Leaders/Project Leaders | 0% | 0 hrs | 4 days | Mon 11/25/13 | Mon 12/2/13 | 16,17
Senior Management Approval for Remediation Plan | 0% | 0 hrs | 5 days | Tue 12/3/13 | Mon 12/9/13 | 18
Senior Management Approval of ICD-10 Project Remediation Budget | 0% | 0 hrs | 5 days | Tue 12/3/13 | Mon 12/9/13 | 18
Document & Finalize Project Logistics | 0% | 0 hrs | 4 days | Mon 10/28/13 | Thu 10/31/13
Validate/Develop logistics process for Laptops, rooms, facilities to support program as well as hire/fire procedures for consultants | 0% | 0 hrs | 4 days | Mon 10/28/13 | Thu 10/31/13 | 4
Project Kickoff | 0% | 0 hrs | 11.5 days | Tue 12/10/13 | Thu 12/26/13
Develop, Iterate & Review Kickoff Presentation | 0% | 0 hrs | 10 days | Tue 12/10/13 | Mon 12/23/13 | 14
Execute Project Kickoff across teams | 0% | 0 hrs | 1 day | Tue 12/24/13 | Thu 12/26/13 | 24
Develop a System Wide Communication Plan | 0% | 0 hrs | 10 days | Mon 10/28/13 | Fri 11/8/13
Develop/Review a plan to build ICD-10 awareness for all hospital employees and key external stakeholders such as non-employed physicians. | 0% | 0 hrs | 10 days | Mon 10/28/13 | Fri 11/8/13 | 4
Phase 3 - Remediate | 0% | 348 hrs | 457 days | Tue 5/28/13 | Wed 3/18/15
Operations | 1% | 328 hrs | 338 days | Tue 9/3/13 | Tue 1/6/15
Training and Education | 1% | 0 hrs | 338 days | Tue 9/3/13 | Tue 1/6/15
Project Checklist/Planning | 0% | 0 hrs | 5 days | Tue 11/5/13 | Mon 11/11/13
Review Project Checklist | 0% | 0 hrs | 2 days | Tue 11/5/13 | Wed 11/6/13
Determine which tasks have been completed | 0% | 0 hrs | 1 day | Thu 11/7/13 | Thu 11/7/13 | 32
Complete checklist | 0% | 0 hrs | 1 day | Fri 11/8/13 | Fri 11/8/13 | 33
Submit Project checklist to Program Director | 0% | 0 hrs | 1 day | Mon 11/11/13 | Mon 11/11/13 | 34
Education and Training Committee to oversee ICD-10 implementation | 0% | 0 hrs | 13 days | Tue 11/19/13 | Mon 12/9/13
Identify Education and Training Committee members | 0% | 0 hrs | 2 days | Tue 11/19/13 | Wed 11/20/13
Establish Committee Charter | 0% | 0 hrs | 10 days | Thu 11/21/13 | Fri 12/6/13 | 37
Schedule recurring monthly meetings to review progress | 0% | 0 hrs | 1 day | Mon 12/9/13 | Mon 12/9/13 | 38
Create ICD-10 code awareness for education & training program | 0% | 0 hrs | 275 days | Tue 12/3/13 | Tue 1/6/15
Define key awareness messages and timing | 0% | 0 hrs | 10 days | Tue 12/3/13 | Mon 12/16/13
Integrate into program communication plan | 0% | 0 hrs | 20 days | Tue 12/17/13 | Wed 1/15/14 | 41
Execute awareness campaign | 0% | 0 hrs | 245 days | Thu 1/16/14 | Tue 1/6/15 | 42
Implementation Plan Development | 45% | 0 hrs | 11 days | Tue 12/3/13 | Tue 12/17/13
Develop the implementation plan | 100% | 0 hrs | 5 days | Tue 12/3/13 | Mon 12/9/13
Obtain final approval from stakeholders | 0% | 0 hrs | 5 days | Tue 12/10/13 | Mon 12/16/13 | 45
Execute the final implementation plan | 0% | 0 hrs | 1 day | Tue 12/17/13 | Tue 12/17/13 | 46
Initial on-site Kickoff Meeting | 0% | 0 hrs | 40 days | Tue 11/19/13 | Fri 1/17/14
Identify individual groups who will participate in the initial kick-off meeting | 0% | 0 hrs | 15 days | Tue 11/19/13 | Wed 12/11/13
Schedule ICD-10 kick-off meetings for the individual groups | 0% | 0 hrs | 5 days | Thu 12/12/13 | Wed 12/18/13 | 49
Execute the ICD-10 individual group meetings | 0% | 0 hrs | 20 days | Thu 12/19/13 | Fri 1/17/14 | 50
Coder Education Assessment and report of results | 100% | 0 hrs | 7 days | Tue 9/3/13 | Wed 9/11/13
Identify individuals who will participate in the Coder Assessment | 100% | 0 hrs | 1 day | Tue 9/3/13 | Tue 9/3/13
Schedule the Coder Assessment | 100% | 0 hrs | 1 day | Wed 9/4/13 | Wed 9/4/13 | 53
Conduct the assessment | 100% | 0 hrs | 3 days | Thu 9/5/13 | Mon 9/9/13 | 54
Schedule a meeting to review the Coder Assessment | 100% | 0 hrs | 1 day | Tue 9/10/13 | Tue 9/10/13 | 55
Review the Coder Assessment results | 100% | 0 hrs | 1 day | Wed 9/11/13 | Wed 9/11/13 | 56
Documentation Assessment & Report | 0% | 0 hrs | 35 days | Tue 1/7/14 | Mon 2/24/14
Determine when the coding documentation review will occur | 0% | 0 hrs | 1 day | Tue 1/7/14 | Tue 1/7/14
Schedule the Documentation Review | 0% | 0 hrs | 0 days | Tue 1/7/14 | Tue 1/7/14 | 59
Identify the medical records to review | 0% | 0 hrs | 0 days | Tue 1/7/14 | Tue 1/7/14 | 60
Perform the documentation review | 0% | 0 hrs | 0 days | Tue 1/7/14 | Tue 1/7/14 | 61
Identify the educational opportunities from the medical records | 0% | 0 hrs | 0 days | Tue 1/7/14 | Tue 1/7/14 | 62
Conduct education with coders and/or providers based on the documentation review | 0% | 0 hrs | 0 days | Tue 1/7/14 | Tue 1/7/14 | 63
Provide a comprehensive final report that contains recommendations and areas of improvement based on the findings | 0% | 0 hrs | 1 day | Mon 2/24/14 | Mon 2/24/14 | 64
ICD-10 Training Roster | 0% | 0 hrs | 55 days | Tue 12/3/13 | Wed 2/19/14
Obtain final approval for coder roster | 0% | 0 hrs | 5 days | Tue 12/3/13 | Mon 12/9/13
Obtain final approval for provider roster | 0% | 0 hrs | 5 days | Tue 12/10/13 | Mon 12/16/13
Obtain final approval for "other staff" roster | 0% | 0 hrs | 5 days | Wed 2/12/14 | Tue 2/18/14
Distribute final coding roster | 0% | 0 hrs | 1 day | Tue 12/10/13 | Tue 12/10/13 | 67
Distribute final provider roster | 0% | 0 hrs | 1 day | Tue 12/17/13 | Tue 12/17/13 | 68
Distribute final Other Staff roster | 0% | 0 hrs | 1 day | Wed 2/19/14 | Wed 2/19/14 | 69
ICD-10 Education Plans | 0% | 0 hrs | 79 days | Tue 12/10/13 | Tue 4/1/14
Develop coder individualized educational plans | 0% | 0 hrs | 25 days | Tue 12/10/13 | Wed 1/15/14 | 67
Develop provider individualized educational plans | 0% | 0 hrs | 25 days | Tue 12/17/13 | Wed 1/22/14 | 68
Develop "other staff" individualized educational plans | 0% | 0 hrs | 25 days | Wed 2/19/14 | Tue 3/25/14 | 69
Obtain final approval for coder education plan | 0% | 0 hrs | 5 days | Thu 1/16/14 | Wed 1/22/14 | 74
Obtain final approval for physician education plan | 0% | 0 hrs | 5 days | Thu 1/23/14 | Wed 1/29/14 | 75
Obtain final approval for "other staff" education plan | 0% | 0 hrs | 5 days | Wed 3/26/14 | Tue 4/1/14 | 76
Distribute final ICD-10 education plan to Committee | 0% | 0 hrs | 5 days | Thu 1/16/14 | Wed 1/22/14 | 74
ICD-10 Coder Education | 0% | 0 hrs | 125 days | Mon 1/6/14 | Mon 6/30/14
Phase I ICD-10 education | 0% | 0 hrs | 25 days | Mon 1/6/14 | Fri 2/7/14
Phase II ICD-10 education | 0% | 0 hrs | 25 days | Mon 2/10/14 | Fri 3/14/14 | 82
Phase III ICD-10 education | 0% | 0 hrs | 25 days | Mon 3/17/14 | Fri 4/18/14 | 83
Phase IV ICD-10 education | 0% | 0 hrs | 25 days | Mon 4/21/14 | Fri 5/23/14 | 84
Phase V ICD-10 education | 0% | 0 hrs | 25 days | Tue 5/27/14 | Mon 6/30/14 | 85
ICD-10 Provider Education | 0% | 0 hrs | 125 days | Mon 1/6/14 | Mon 6/30/14
Phase I ICD-10 education | 0% | 0 hrs | 25 days | Mon 1/6/14 | Fri 2/7/14
Phase II ICD-10 education | 0% | 0 hrs | 25 days | Mon 2/10/14 | Fri 3/14/14 | 88
Phase III ICD-10 education | 0% | 0 hrs | 25 days | Mon 3/17/14 | Fri 4/18/14 | 89
Phase IV ICD-10 education | 0% | 0 hrs | 25 days | Mon 4/21/14 | Fri 5/23/14 | 90
Phase V ICD-10 education | 0% | 0 hrs | 25 days | Tue 5/27/14 | Mon 6/30/14 | 91
ICD-10 Other Staff Education | 0% | 0 hrs | 100.16 days | Tue 4/29/14 | Fri 9/19/14
Phase I ICD-10 education | 0% | 0 hrs | 20 days | Tue 4/29/14 | Tue 5/27/14
Phase II ICD-10 education | 0% | 0 hrs | 20 days | Wed 5/28/14 | Tue 6/24/14 | 94
Phase III ICD-10 education | 0% | 0 hrs | 20 days | Wed 6/25/14 | Wed 7/23/14 | 95
Phase IV ICD-10 education | 0% | 0 hrs | 20.16 days | Thu 7/24/14 | Thu 8/21/14 | 96
Phase V ICD-10 education | 0% | 0 hrs | 20 days | Thu 8/21/14 | Fri 9/19/14 | 97
Mid-point/Interim Session | 0% | 0 hrs | 22 days | Wed 3/12/14 | Thu 4/10/14
Schedule meeting to discuss training and education progress | 0% | 0 hrs | 7 days | Wed 3/12/14 | Thu 3/20/14
Conduct mid-point meeting to discuss progress | 0% | 0 hrs | 15 days | Fri 3/21/14 | Thu 4/10/14 | 100
Productivity and Parallel Coding | 0% | 328 hrs | 188 days | Tue 1/7/14 | Tue 9/30/14
Coding Staffing Validation | 0% | 80 hrs | 50 days | Mon 2/10/14 | Fri 4/18/14
Schedule meeting to discuss coding retention strategy | 0% | 8 hrs | 5 days | Mon 2/10/14 | Fri 2/14/14
Validate approach to secure coding positions | 0% | 8 hrs | 5 days | Mon 2/17/14 | Fri 2/21/14 | 104
Develop strategy for implement coding retention strategy | 0% | 40 hrs | 20 days | Mon 2/24/14 | Fri 3/21/14 | 105
Implement strategy to retain coding staff | 0% | 24 hrs | 20 days | Mon 3/24/14 | Fri 4/18/14 | 106
Parallel Coding | 0% | 236 hrs | 188 days | Tue 1/7/14 | Tue 9/30/14
Schedule meeting to discuss Parallel Coding Strategy | 0% | 1 hr | 5 days | Tue 1/7/14 | Mon 1/13/14
Validate the percentage of inpatient records that will be included in parallel coding | 0% | 4 hrs | 5 days | Mon 1/20/14 | Fri 1/24/14 | 109
Validate the percentage of outpatient visits that will be included in parallel coding | 0% | 4 hrs | 5 days | Mon 1/20/14 | Fri 1/24/14 | 109
Determine when parallel coding will begin | 0% | 2 hrs | 5 days | Mon 1/27/14 | Fri 1/31/14 | 111
Develop parallel coding strategy to support the concept | 0% | 40 hrs | 20 days | Mon 2/3/14 | Fri 2/28/14 | 112
Determine how feedback will be given to providers when documentation does not support ICD-10 coding | 0% | 2 hrs | 20 days | Mon 2/3/14 | Fri 2/28/14
Schedule weekly meetings after parallel coding begins | 0% | 2 hrs | 5 days | Mon 3/3/14 | Fri 3/7/14 | 114
Execute parallel coding | 0% | 181 hrs | 64 days | Tue 7/1/14 | Tue 9/30/14
Training and Education Wrap Up Session | 0% | 12 hrs | 15 days | Mon 9/8/14 | Fri 9/26/14
Schedule meeting to discuss the wrap up of training and education | 0% | 4 hrs | 5 days | Mon 9/8/14 | Fri 9/12/14
Conduct wrap up meeting with training and education | 0% | 8 hrs | 5 days | Mon 9/22/14 | Fri 9/26/14
Revenue Cycle | 0% | 0 hrs | 355 days | Mon 10/21/13 | Wed 3/18/15
Payor Monitoring | 0% | 0 hrs | 355 days | Mon 10/21/13 | Wed 3/18/15
Assign payors to risk groups Tier 1 (largest impact) and Tier 2 | 0% | 0 hrs | 5 days | Mon 10/21/13 | Fri 10/25/13
Send payor readiness survey to payors | 0% | 0 hrs | 10 days | Mon 10/28/13 | Fri 11/8/13 | 122
Create call scripts, based on feedback from initial survey/call, for on-going discussions with payors | 0% | 0 hrs | 14 days | Mon 11/11/13 | Mon 12/2/13 | 123
Initiate contact with all contracted payors at outset to discuss remediation efforts and receive available documentation of their timelines | 0% | 0 hrs | 15 days | Mon 10/21/13 | Fri 11/8/13
Identify payors that will convert to ICD-10 by go-live date versus those that will not be ready by the go-live date | 0% | 0 hrs | 15 days | Mon 11/11/13 | Tue 12/3/13 | 125
Determine which payors will be ready for dual processing and estimated timing | 0% | 0 hrs | 15 days | Mon 11/11/13 | Tue 12/3/13
Identify payor testing schedule and vendor/business partner readiness | 0% | 0 hrs | 15 days | Mon 11/11/13 | Tue 12/3/13
Develop schedule of contacts (e.g. Tier 1 monthly, Tier 2 bi-monthly) | 0% | 0 hrs | 15 days | Mon 11/11/13 | Tue 12/3/13
Create/revise tools and templates for tracking, monitoring, and reporting status | 0% | 0 hrs | 5 days | Mon 11/11/13 | Fri 11/15/13
Identify plan for payors not required to move to ICD-10 (e.g. auto insurance, worker's compensation) | 0% | 0 hrs | 5 days | Mon 11/11/13 | Fri 11/15/13
Develop risk mitigation strategy and coordinate with IT for those payors not required to move to ICD-10 | 0% | 0 hrs | 20 days | Mon 11/18/13 | Tue 12/17/13 | 131
Monitor performance of each payor under dual processing | 0% | 0 hrs | 315 days | Wed 12/18/13 | Wed 3/18/15 | 132
Monitor and track status of payor testing and reporting (weekly) | 0% | 0 hrs | 315 days | Wed 12/18/13 | Wed 3/18/15 | 132
Update payor management strategy and plan, as needed (monthly) | 0% | 0 hrs | 315 days | Wed 12/18/13 | Wed 3/18/15 | 132
Updates to contract language (Per Payor) | 0% | 0 hrs | 155 days | Mon 10/21/13 | Fri 5/30/14
Coordinate with Legal on development methods to mitigate cash flow and revenue risks | 0% | 0 hrs | 15 days | Mon 10/21/13 | Fri 11/8/13
Negotiate revenue neutrality principles/methodologies in contracts | 0% | 0 hrs | 140 days | Mon 11/11/13 | Fri 5/30/14 | 137
Determine how payor changes may affect pre-authorization and/or medical necessity requirements | 0% | 0 hrs | 15 days | Mon 10/21/13 | Fri 11/8/13
Determine potential remediation options for payment delays | 0% | 0 hrs | 45 days | Mon 10/21/13 | Tue 12/24/13
Create core requirements for modified contract terms | 0% | 0 hrs | 30 days | Mon 11/11/13 | Tue 12/24/13 | 137
Coordinate Payer Testing with IT by Tier (Align with IT Testing) | 0% | 0 hrs | 155 days | Mon 3/3/14 | Wed 10/8/14
Coordinate payor proposed integrated testing with IT | 0% | 0 hrs | 155 days | Mon 3/3/14 | Wed 10/8/14
Establish baseline for productivity standards and outcomes for critical areas | 0% | 0 hrs | 60 days | Mon 10/28/13 | Thu 1/23/14
Establish baseline for productivity standards and outcomes in case management | 0% | 0 hrs | 15 days | Mon 10/28/13 | Fri 11/15/13
Establish baseline for productivity standards and outcomes in claims processing | 0% | 0 hrs | 15 days | Mon 10/28/13 | Fri 11/15/13
Establish baseline for productivity standards and outcomes in authorization services | 0% | 0 hrs | 15 days | Mon 10/28/13 | Fri 11/15/13
Review productivity standards and outcomes in case management | 0% | 0 hrs | 15 days | Mon 11/18/13 | Tue 12/10/13 | 147
Review productivity standards and outcomes in claims processing | 0% | 0 hrs | 15 days | Mon 11/18/13 | Tue 12/10/13 | 147
Review productivity standards and outcomes in authorization services | 0% | 0 hrs | 15 days | Mon 11/18/13 | Tue 12/10/13 | 147
Determine additional resources/cost relative to ICD-10in case management | 0% | 0 hrs | 30 days | Wed 12/11/13 | Thu 1/23/14 | 150
Determine additional resources/cost relative to ICD-10in claims processing | 0% | 0 hrs | 30 days | Wed 12/11/13 | Thu 1/23/14 | 150
Determine additional resources/cost relative to ICD-10 in authorization services | 0% | 0 hrs | 30 days | Wed 12/11/13 | Thu 1/23/14 | 150
Pursue strategies to enhance cash on hand | 0% | 0 hrs | 60 days | Mon 10/28/13 | Thu 1/23/14
Project financial risk based on feedback by major payor | 0% | 0 hrs | 45 days | Mon 10/28/13 | Thu 1/2/14
Confirm trends in days cash on hand/cash reserves | 0% | 0 hrs | 15 days | Mon 10/28/13 | Fri 11/15/13
Identify measures to solidify cash flow in the event of negative impact related to ICD 10 cutover | 0% | 0 hrs | 15 days | Mon 10/28/13 | Fri 11/15/13
Determine processes to monitor/report revenue realization and projections | 0% | 0 hrs | 15 days | Mon 11/18/13 | Tue 12/10/13 | 157
Establish baseline and estimate low-medium-high impact related to ICD 10 cutover | 0% | 0 hrs | 30 days | Mon 10/28/13 | Tue 12/10/13
Determine processes to monitor/model/report accounts receivables | 0% | 0 hrs | 30 days | Mon 10/28/13 | Tue 12/10/13
Determine processes to monitor/model/report bad debt reserves | 0% | 0 hrs | 30 days | Mon 10/28/13 | Tue 12/10/13
Develop/refine monthly operating and cash flow forecast/budget | 0% | 0 hrs | 30 days | Wed 12/11/13 | Thu 1/23/14 | 161
Review all pending capital expenses to understand financial commitments | 0% | 0 hrs | 15 days | Mon 10/28/13 | Fri 11/15/13
Denials management program enhancement - Inpatient, Outpatient, Physician | 0% | 0 hrs | 291 days | Mon 11/4/13 | Tue 12/30/14
Inventory denials management policies and procedures | 0% | 0 hrs | 1 day | Mon 11/4/13 | Mon 11/4/13
Inventory performance metrics related to denials | 0% | 0 hrs | 1 day | Mon 11/4/13 | Mon 11/4/13
Revise policies, procedures and performance metrics as needed | 0% | 0 hrs | 1 day | Mon 11/4/13 | Mon 11/4/13
Identify any technology resources that will assist in denials process (e.g., automated claims status) | 0% | 0 hrs | 45 days | Mon 11/4/13 | Thu 1/9/14
Identify current denial patterns associated with specific codes and develop trends analysis (focus: no authorization, medical necessity, local coverage determinations, national coverage determinations, coverage policy bulletins, additional documentation | 0% | 0 hrs | 45 days | Mon 11/18/13 | Thu 1/23/14
Implement/refine process changes to prevent and avoid denials | 0% | 0 hrs | 30 days | Fri 1/24/14 | Thu 3/6/14 | 169
Monitor and identify new patterns of denials associated with ICD-10 codes | 0% | 0 hrs | 30 days | Fri 1/24/14 | Thu 3/6/14 | 169
Develop process improvement plan for denials and challenge with the payor as necessary | 0% | 0 hrs | 200 days | Fri 3/7/14 | Thu 12/18/14 | 171
Provide findings to monthly Revenue Cycle Team (ICD-10 MISSION CONTROL TEAM) | 0% | 0 hrs | 250 days | Mon 1/6/14 | Tue 12/30/14
ICD-10 MISSION CONTROL (Revenue Cycle Teams) - Focus, Develop and Monitor | 0% | 0 hrs | 342 days | Mon 11/4/13 | Fri 3/13/15
Incorporate ICD-10 related tasks and objectives into revenue cycle committee (sub-name ICD-10 MISSION CONTROL TEAM) | 0% | 0 hrs | 1 day | Mon 11/4/13 | Mon 11/4/13
Establish MISSION CONTROL objectives, tools and processes relative to ICD-10 | 0% | 0 hrs | 60 days | Mon 11/4/13 | Thu 1/30/14
Identify DNFB targets and other cash flow related targets | 0% | 0 hrs | 60 days | Mon 11/4/13 | Thu 1/30/14
Break DNFB and other cash flow targets into smaller actionable buckets for reporting and process work (e.g. DNFB uncoded, admitting errors, non-HIM holds, related to physician queries, documentation requests, report dictation or history/physical) | 0% | 0 hrs | 60 days | Mon 11/4/13 | Thu 1/30/14
Identify Days in A/R target | 0% | 0 hrs | 60 days | Wed 11/20/13 | Mon 2/17/14 | 188
Develop/refine process flows for all relevant sub-processes relative to DNFB and other cash flow metrics | 0% | 0 hrs | 60 days | Tue 2/18/14 | Mon 5/12/14 | 179
Develop/refine a dashboard to track DNFB and other cash flow metrics based defined root cause delays | 0% | 0 hrs | 60 days | Tue 5/13/14 | Wed 8/6/14 | 180
Actively communicate DNFB and other cash flow measures to key stakeholders and ensure accountability | 0% | 0 hrs | 150 days | Thu 8/7/14 | Fri 3/13/15 | 181
Run weekly A/R reports by payors to get an understanding of the A/R inventory pre ICD-10 | 0% | 0 hrs | 210 days | Tue 5/13/14 | Fri 3/13/15 | 180
Review A/R fluctuations to determine the impact on billing and processing of claims | 0% | 0 hrs | 210 days | Tue 5/13/14 | Fri 3/13/15 | 180
Review weekly A/R reports to track any A/R fluctuations in relation to ICD-10 | 0% | 0 hrs | 210 days | Tue 5/13/14 | Fri 3/13/15 | 180
Identify/report where specific issues that may have a negative financial impact post implementation | 0% | 0 hrs | 210 days | Tue 5/13/14 | Fri 3/13/15 | 180
Implement corrective action to mediate the issues | 0% | 0 hrs | 210 days | Tue 5/13/14 | Fri 3/13/15 | 180
Develop the process to discharge recurring accounts on September 30th, 2014 | 0% | 0 hrs | 11 days | Tue 11/5/13 | Tue 11/19/13 | 175
Implement the process to discharge recurring accounts on September 30th, 2014 | 0% | 0 hrs | 10 days | Tue 9/30/14 | Mon 10/13/14
Identify all recurring /serial accounts and continue to process weekly updates for patients that will receive treatment over the cutover period | 0% | 0 hrs | 14 days | Mon 7/7/14 | Thu 7/24/14
Develop process to readmit active recurring accounts on October 1st, 2014 | 0% | 0 hrs | 1 day | Mon 9/15/14 | Mon 9/15/14
Readmit active recurring accounts on October 1st, 2014 | 0% | 0 hrs | 10 days | Wed 10/1/14 | Tue 10/14/14
Recode recurring accounts using ICD-10 codes beginning October 1st, 2014 | 0% | 0 hrs | 15 days | Wed 10/1/14 | Tue 10/21/14
Compliance - Policy & Procedure | 0% | 0 hrs | 331 days | Fri 10/4/13 | Wed 1/28/15
Establish processes such that relevant stakeholders throughout the organization receive compliance materials (Local Coverage Determination) and take ownership (sign-off) to ensure implications are processed and appropriate changes implemented | 0% | 0 hrs | 331 days | Fri 10/4/13 | Wed 1/28/15
Identify Central person to manage Local Coverage Determinations (LCDs) | 0% | 0 hrs | 1 day | Mon 10/28/13 | Mon 10/28/13
Document current process flow related to LCDs | 0% | 0 hrs | 14 days | Tue 10/29/13 | Fri 11/15/13 | 196
Review all current LCDs | 0% | 0 hrs | 14 days | Tue 10/29/13 | Fri 11/15/13 | 196
Join list serve to ensure all relevant changes to LCD are communicated to central person | 0% | 0 hrs | 5 days | Tue 10/29/13 | Mon 11/4/13
Relate LCDs to relevant parties/departments | 0% | 0 hrs | 21 days | Mon 11/18/13 | Wed 12/18/13 | 198
Develop communication preparing parties of new expectations relative to LCDs | 0% | 0 hrs | 1 day | Mon 11/4/13 | Mon 11/4/13
Send communication preparing parties of new expectations relative to LCDs | 0% | 0 hrs | 1 day | Tue 11/5/13 | Tue 11/5/13 | 201
Distribute relevant LCDs to parties/departments | 0% | 0 hrs | 5 days | Wed 11/6/13 | Tue 11/12/13 | 202
Develop policy for pertinent parties to sign off reflecting their review and integration of LCDs | 0% | 0 hrs | 30 days | Mon 11/4/13 | Tue 12/17/13
Develop sign-off form that validates review and integration of LCD info into operations | 0% | 0 hrs | 5 days | Wed 12/18/13 | Tue 12/24/13 | 204
Monitor for LCD changes | 0% | 0 hrs | 315 days | Mon 10/28/13 | Wed 1/28/15
Send all LCD changes to pertinent parties | 0% | 0 hrs | 315 days | Fri 10/4/13 | Tue 1/6/15
Document new process flow | 0% | 0 hrs | 14 days | Wed 12/18/13 | Wed 1/8/14 | 204
Track to ensure pertient party signs off that they have reviewed and integrated, as appropriate, into operations | 0% | 0 hrs | 315 days | Mon 10/28/13 | Wed 1/28/15
Outpatient physical, occupational and speech therapy treating diagnoses | 0% | 0 hrs | 282 days | Mon 10/28/13 | Mon 12/8/14
Assign a functional owner to the process of assigning and coding treating diagnoses in the outpatient setting | 0% | 0 hrs | 7 days | Mon 10/28/13 | Tue 11/5/13
Document the current process flow for therapists assigining treating diagnoses | 0% | 0 hrs | 21 days | Wed 11/6/13 | Fri 12/6/13 | 211
Orient therapists to regulatory guidance regarding assignment of trating diagnoses | 0% | 0 hrs | 30 days | Mon 12/9/13 | Tue 1/21/14 | 212
Assess consistency of documentation currently for capturing treating diagnoses | 0% | 0 hrs | 14 days | Wed 1/22/14 | Mon 2/10/14 | 213
Determine process to ensure consistency of physician signature on plan of care | 0% | 0 hrs | 15 days | Tue 2/11/14 | Mon 3/3/14 | 214
Determine revised process for coding treating diagnoses | 0% | 0 hrs | 14 days | Mon 10/28/13 | Thu 11/14/13
Orient coders to all sources of documentation to capture treating and medical diagnoses | 0% | 0 hrs | 14 days | Fri 11/15/13 | Fri 12/6/13 | 216
Develop process for timely claims submission including all relevant diagnoses codes | 0% | 0 hrs | 14 days | Fri 11/15/13 | Fri 12/6/13
Document new process flow | 0% | 0 hrs | 14 days | Mon 12/23/13 | Mon 1/13/14 | 218
Monitor effectiveness of revised process flow | 0% | 0 hrs | 230 days | Tue 1/14/14 | Mon 12/8/14 | 219
Reference Sheets | 0% | 0 hrs | 296 days | Mon 11/4/13 | Thu 1/8/15
Identify all reference sheets (paper or electronic sources of information from which diagnoses are pulled in the registration or authorization process) | 0% | 0 hrs | 1 day | Mon 11/4/13 | Mon 11/4/13
Document the current process flow related to reference sheets | 0% | 0 hrs | 14 days | Tue 11/5/13 | Fri 11/22/13 | 222
Determine the overlap of data sources | 0% | 0 hrs | 1 day | Mon 11/25/13 | Mon 11/25/13 | 223
Refine data to meet specific needs of clients | 0% | 0 hrs | 7 days | Tue 11/26/13 | Fri 12/6/13 | 224
Remediate all reference sheets to ICD-10 | 0% | 0 hrs | 30 days | Mon 12/9/13 | Tue 1/21/14 | 225
Orient pertinent staff for correct use of revised reference sheets | 0% | 0 hrs | 14 days | Wed 1/22/14 | Mon 2/10/14 | 226
Design process for changes in reference sheets on an ongoing basis | 0% | 0 hrs | 15 days | Tue 2/11/14 | Mon 3/3/14 | 227
Document new process flow | 0% | 0 hrs | 14 days | Tue 3/4/14 | Fri 3/21/14 | 228
Monitor effectiveness of revised process flow. | 0% | 0 hrs | 125 days | Mon 3/24/14 | Wed 9/17/14 | 229
Report findings to MISSION CONTROL TEAM | 0% | 0 hrs | 200 days | Mon 3/24/14 | Thu 1/8/15 | 229
Information Technology (IT) | 0% | 20 hrs | 385 days | Tue 5/28/13 | Tue 12/2/14
Develop Test Strategy & Approach | 0% | 20 hrs | 162 days | Tue 5/28/13 | Thu 1/16/14
Identify and Document Data Flow | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
Meditech Magic | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
3M CRS | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
Rapid | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
Midas | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
eMDs | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
Truven | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
Maestro | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
CraneWare | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
Point Click Care | 0% | 0 hrs | 20 days | Tue 10/1/13 | Mon 10/28/13
Develop Test Strategy | 0% | 20 hrs | 90 days | Tue 5/28/13 | Wed 10/2/13
Create Test Strategy DRAFT | 0% | 0 hrs | 15 days | Tue 5/28/13 | Mon 6/17/13
Creat Test Strategy FINAL | 0% | 20 hrs | 10 days | Thu 9/19/13 | Wed 10/2/13 | 245
Develop Test Plan & Test Scenarios | 0% | 0 hrs | 70 days | Mon 10/7/13 | Thu 1/16/14
Analysis of the current TEST Environment capabilities | 0% | 0 hrs | 10 days | Mon 10/7/13 | Fri 10/18/13
Publish any projected changes to those TEST regions | 0% | 0 hrs | 10 days | Mon 10/21/13 | Fri 11/1/13 | 248
Validate and Tier Payor Inventory | 0% | 0 hrs | 20 days | Mon 11/4/13 | Tue 12/3/13 | 249
Test Plan Schedule | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14
Meditech Magic | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
3M CRS | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
Rapid | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
Midas | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
eMDs | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
Truven | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
Maestro | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
CraneWare | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
Point Click Care | 0% | 0 hrs | 20 days | Wed 12/4/13 | Thu 1/2/14 | 250
Create the Payor Test Data Preparation Plan | 0% | 0 hrs | 15 days | Wed 12/4/13 | Tue 12/24/13 | 250
Validate Payor Readiness Schedule | 0% | 0 hrs | 15 days | Thu 12/26/13 | Thu 1/16/14 | 261
Remeditate Systems | 0% | 0 hrs | 152 days | Mon 10/7/13 | Mon 5/12/14
Meditech | 0% | 0 hrs | 94 days | Mon 10/7/13 | Wed 2/19/14
Validate Readiness | 0% | 0 hrs | 10 days | Mon 10/7/13 | Fri 10/18/13
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Mon 10/7/13 | Fri 10/18/13
Requirements & Design | 0% | 0 hrs | 4 days | Mon 10/21/13 | Thu 10/24/13
Validate technology requirements and system dependencies from vendor to facilitate upgrade | 0% | 0 hrs | 4 days | Mon 10/21/13 | Thu 10/24/13 | 266
Installation & Build | 0% | 0 hrs | 26 days | Fri 10/25/13 | Tue 12/3/13
Execute any applicable system modifications | 0% | 0 hrs | 1 day | Fri 10/25/13 | Fri 10/25/13 | 268
Modify Interfaces | 0% | 0 hrs | 20 days | Mon 11/4/13 | Tue 12/3/13
Mirth | 0% | 0 hrs | 20 days | Mon 11/4/13 | Tue 12/3/13
Iatrics | 0% | 0 hrs | 20 days | Mon 11/4/13 | Tue 12/3/13
Modify Files for Export | 0% | 0 hrs | 4 days | Mon 10/28/13 | Thu 10/31/13
Files exported to Truven | 0% | 0 hrs | 4 days | Mon 10/28/13 | Thu 10/31/13 | 270
Testing | 0% | 0 hrs | 80 days | Mon 10/7/13 | Thu 1/30/14
Execute system and/or interface testing | 0% | 0 hrs | 30 days | Mon 10/7/13 | Fri 11/15/13
Execute Integration Testing (end-to-end) | 0% | 0 hrs | 30 days | Mon 11/18/13 | Thu 1/2/14 | 277
Manange, Track and Remediate Defects | 0% | 0 hrs | 20 days | Fri 1/3/14 | Thu 1/30/14 | 278
Support & Go Live Planning | 0% | 0 hrs | 14 days | Fri 1/31/14 | Wed 2/19/14
Define team to support solution in stabilization phase | 0% | 0 hrs | 3 days | Fri 1/31/14 | Tue 2/4/14 | 279
Execute Production Cutover Activities/Vendor Migration | 0% | 0 hrs | 10 days | Wed 2/5/14 | Tue 2/18/14 | 281
Product Go Live | 0% | 0 hrs | 1 day | Wed 2/19/14 | Wed 2/19/14 | 282
3M CRS - Coding and Reimbursement System | 0% | 0 hrs | 69 days | Mon 10/7/13 | Wed 1/15/14
Validate Readiness | 0% | 0 hrs | 10 days | Mon 10/7/13 | Fri 10/18/13
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Mon 10/7/13 | Fri 10/18/13
Requirements & Design | 0% | 0 hrs | 4 days | Mon 10/21/13 | Thu 10/24/13
Validate technology requirements and system dependencies from vendor to facilitate upgrade | 0% | 0 hrs | 4 days | Mon 10/21/13 | Thu 10/24/13 | 286
Installation & Build | 0% | 0 hrs | 1 day | Fri 10/25/13 | Fri 10/25/13
Execute any applicable system modifications | 0% | 0 hrs | 1 day | Fri 10/25/13 | Fri 10/25/13 | 288
Testing | 0% | 0 hrs | 40 days | Mon 10/28/13 | Tue 12/24/13
Execute system and/or interface testing | 0% | 0 hrs | 15 days | Mon 10/28/13 | Fri 11/15/13 | 290
Execute Integration Testing (end-to-end) | 0% | 0 hrs | 15 days | Mon 11/18/13 | Tue 12/10/13 | 292
Manange, Track and Remediate Defects | 0% | 0 hrs | 10 days | Wed 12/11/13 | Tue 12/24/13 | 293
Support & Go Live Planning | 0% | 0 hrs | 14 days | Thu 12/26/13 | Wed 1/15/14
Define team to support solution in stabilization phase | 0% | 0 hrs | 3 days | Thu 12/26/13 | Mon 12/30/13 | 294
Execute Production Cutover Activities/Vendor Migration | 0% | 0 hrs | 10 days | Tue 12/31/13 | Tue 1/14/14 | 296
Product Go Live | 0% | 0 hrs | 1 day | Wed 1/15/14 | Wed 1/15/14 | 297
Truven | 0% | 0 hrs | 56 days | Thu 1/2/14 | Thu 3/20/14
Validate Readiness | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Requirements & Design | 0% | 0 hrs | 4 days | Thu 1/16/14 | Tue 1/21/14
Validate technology requirements and system dependencies from vendor to facilitate upgrade | 0% | 0 hrs | 4 days | Thu 1/16/14 | Tue 1/21/14 | 301
Installation and Build | 0% | 0 hrs | 1 day | Wed 1/22/14 | Wed 1/22/14
Execute any applicable system modifications | 0% | 0 hrs | 1 day | Wed 1/22/14 | Wed 1/22/14 | 303
Testing | 0% | 0 hrs | 40 days | Thu 1/23/14 | Wed 3/19/14
Execute system and/or interface testing | 0% | 0 hrs | 15 days | Thu 1/23/14 | Wed 2/12/14 | 305
Execute Integration Testing (end-to-end) | 0% | 0 hrs | 15 days | Thu 2/13/14 | Wed 3/5/14 | 307
Manange, Track and Remediate Defects | 0% | 0 hrs | 10 days | Thu 3/6/14 | Wed 3/19/14 | 308
Support & Go Live Planning | 0% | 0 hrs | 1 day | Thu 3/20/14 | Thu 3/20/14
Product Go Live | 0% | 0 hrs | 1 day | Thu 3/20/14 | Thu 3/20/14 | 309
Midas | 0% | 0 hrs | 56 days | Thu 1/2/14 | Thu 3/20/14
Validate Readiness | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Requirements & Design | 0% | 0 hrs | 4 days | Thu 1/16/14 | Tue 1/21/14
Validate technology requirements and system dependencies from vendor to facilitate upgrade | 0% | 0 hrs | 4 days | Thu 1/16/14 | Tue 1/21/14 | 314
Installation and Build | 0% | 0 hrs | 1 day | Wed 1/22/14 | Wed 1/22/14
Execute any applicable system modifications | 0% | 0 hrs | 1 day | Wed 1/22/14 | Wed 1/22/14 | 316
Testing | 0% | 0 hrs | 40 days | Thu 1/23/14 | Wed 3/19/14
Execute system and/or interface testing | 0% | 0 hrs | 15 days | Thu 1/23/14 | Wed 2/12/14 | 318
Execute Integration Testing (end-to-end) | 0% | 0 hrs | 15 days | Thu 2/13/14 | Wed 3/5/14 | 320
Manange, Track and Remediate Defects | 0% | 0 hrs | 10 days | Thu 3/6/14 | Wed 3/19/14 | 321
Support & Go Live Planning | 0% | 0 hrs | 1 day | Thu 3/20/14 | Thu 3/20/14
Product Go Live | 0% | 0 hrs | 1 day | Thu 3/20/14 | Thu 3/20/14 | 322
Rapid | 0% | 0 hrs | 56 days | Thu 1/2/14 | Thu 3/20/14
Validate Readiness | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Requirements & Design | 0% | 0 hrs | 4 days | Thu 1/16/14 | Tue 1/21/14
Validate technology requirements and system dependencies from vendor to facilitate upgrade | 0% | 0 hrs | 4 days | Thu 1/16/14 | Tue 1/21/14 | 327
Installation and Build | 0% | 0 hrs | 1 day | Wed 1/22/14 | Wed 1/22/14
Execute any applicable system modifications | 0% | 0 hrs | 1 day | Wed 1/22/14 | Wed 1/22/14 | 329
Testing | 0% | 0 hrs | 40 days | Thu 1/23/14 | Wed 3/19/14
Execute system and/or interface testing | 0% | 0 hrs | 15 days | Thu 1/23/14 | Wed 2/12/14 | 331
Execute Integration Testing (end-to-end) | 0% | 0 hrs | 15 days | Thu 2/13/14 | Wed 3/5/14 | 333
Manange, Track and Remediate Defects | 0% | 0 hrs | 10 days | Thu 3/6/14 | Wed 3/19/14 | 334
Support & Go Live Planning | 0% | 0 hrs | 1 day | Thu 3/20/14 | Thu 3/20/14
Product Go Live | 0% | 0 hrs | 1 day | Thu 3/20/14 | Thu 3/20/14 | 335
eMDs | 0% | 0 hrs | 56 days | Mon 2/3/14 | Mon 4/21/14
Validate Readiness | 0% | 0 hrs | 10 days | Mon 2/3/14 | Fri 2/14/14
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Mon 2/3/14 | Fri 2/14/14
Requirements & Design | 0% | 0 hrs | 4 days | Mon 2/17/14 | Thu 2/20/14
Validate technology requirements and system dependencies from vendor to facilitate upgrade | 0% | 0 hrs | 4 days | Mon 2/17/14 | Thu 2/20/14 | 340
Installation and Build | 0% | 0 hrs | 1 day | Fri 2/21/14 | Fri 2/21/14
Execute any applicable system modifications | 0% | 0 hrs | 1 day | Fri 2/21/14 | Fri 2/21/14 | 342
Testing | 0% | 0 hrs | 40 days | Mon 2/24/14 | Fri 4/18/14
Execute system and/or interface testing | 0% | 0 hrs | 15 days | Mon 2/24/14 | Fri 3/14/14 | 344
Execute Integration Testing (end-to-end) | 0% | 0 hrs | 15 days | Mon 3/17/14 | Fri 4/4/14 | 346
Manange, Track and Remediate Defects | 0% | 0 hrs | 10 days | Mon 4/7/14 | Fri 4/18/14 | 347
Support & Go Live Planning | 0% | 0 hrs | 1 day | Mon 4/21/14 | Mon 4/21/14
Product Go Live | 0% | 0 hrs | 1 day | Mon 4/21/14 | Mon 4/21/14 | 348
Craneware | 0% | 0 hrs | 55 days | Thu 1/2/14 | Wed 3/19/14
Validate Readiness | 0% | 0 hrs | 30 days | Thu 1/2/14 | Wed 2/12/14
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Ensure required change management plan / marketing plans in place to proactively drive change & adoption based upon process areas impacted & deliver per proposed planned schedule | 0% | 0 hrs | 10 days | Thu 1/16/14 | Wed 1/29/14 | 353
Identify risks, if any, if parallel use is required and system cannot support, availability/process areas impacted concerns | 0% | 0 hrs | 10 days | Thu 1/30/14 | Wed 2/12/14 | 354
Requirements & Design | 0% | 0 hrs | 25 days | Thu 2/13/14 | Wed 3/19/14 | 352
Validate/Define architectural design | 0% | 0 hrs | 9 days | Thu 2/13/14 | Tue 2/25/14
Validate technology requirements and system depenencies from vendor to facilitate upgrade | 0% | 0 hrs | 10 days | Thu 2/13/14 | Wed 2/26/14
Finalize requirements and process dependencies across impacted stakeholders | 0% | 0 hrs | 25 days | Thu 2/13/14 | Wed 3/19/14
Finalize business process changes to support application or interface | 0% | 0 hrs | 25 days | Thu 2/13/14 | Wed 3/19/14
Procurement / Contracts | 0% | 0 hrs | 5 days | Wed 2/26/14 | Tue 3/4/14 | 357
Validate HW/SW/Mtc/Fees - No Cost to support contractual extension/mtc fees or SW | 0% | 0 hrs | 5 days | Wed 2/26/14 | Tue 3/4/14
Installation, Build & Testing | 0% | 0 hrs | 31 days | Mon 1/6/14 | Mon 2/17/14
Identify core infrastructure setup/changes & requirements | 0% | 0 hrs | 10 days | Mon 1/6/14 | Fri 1/17/14
Develop upgrade test plan and deployment plans | 0% | 0 hrs | 15 days | Mon 1/6/14 | Fri 1/24/14
Installation, Testing & Site Deployment | 0% | 0 hrs | 16 days | Mon 1/27/14 | Mon 2/17/14
Upgrade installation execution | 0% | 0 hrs | 5 days | Mon 1/27/14 | Fri 1/31/14 | 365
Execute application and/or interface testing | 0% | 0 hrs | 5 days | Mon 2/3/14 | Fri 2/7/14 | 367
Execute Weekly Checkpoint | 0% | 0 hrs | 5 days | Mon 2/3/14 | Fri 2/7/14 | 367
Execute User Acceptance Testing (UAT) for Process & Technology changes | 0% | 0 hrs | 10 days | Mon 2/3/14 | Fri 2/14/14 | 367
Gain UAT Signoff/Production Readiness | 0% | 0 hrs | 1 day | Fri 2/14/14 | Fri 2/14/14 | 370FF
Execute training to support application changes (Technical) | 0% | 0 hrs | 2 days | Mon 2/10/14 | Tue 2/11/14 | 368
Execute training to support process changes (Business Processes) | 0% | 0 hrs | 10 days | Mon 2/3/14 | Fri 2/14/14 | 367
Execute Production Cutover Activities/Vendor Migration | 0% | 0 hrs | 1 day | Fri 2/14/14 | Fri 2/14/14 | 371FF
Technology documentation to support post implementation mtc | 0% | 0 hrs | 5 days | Mon 2/3/14 | Fri 2/7/14 | 364367
Manange, Track and Remediate Defects | 0% | 0 hrs | 15 days | Mon 1/27/14 | Fri 2/14/14 | 374FF
Product Go Live | 0% | 0 hrs | 1 day | Mon 2/17/14 | Mon 2/17/14 | 374
Point Click Care | 0% | 0 hrs | 55 days | Thu 1/2/14 | Wed 3/19/14
Validate Readiness | 0% | 0 hrs | 30 days | Thu 1/2/14 | Wed 2/12/14
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Thu 1/2/14 | Wed 1/15/14
Ensure required change management plan / marketing plans in place to proactively drive change & adoption based upon process areas impacted & deliver per proposed planned schedule | 0% | 0 hrs | 10 days | Thu 1/16/14 | Wed 1/29/14 | 380
Identify risks, if any, if parallel use is required and system cannot support, availability/process areas impacted concerns | 0% | 0 hrs | 10 days | Thu 1/30/14 | Wed 2/12/14 | 381
Requirements & Design | 0% | 0 hrs | 25 days | Thu 2/13/14 | Wed 3/19/14 | 379
Validate/Define architectural design | 0% | 0 hrs | 9 days | Thu 2/13/14 | Tue 2/25/14
Validate technology requirements and system depenencies from vendor to facilitate upgrade | 0% | 0 hrs | 10 days | Thu 2/13/14 | Wed 2/26/14
Finalize requirements and process dependencies across impacted stakeholders | 0% | 0 hrs | 25 days | Thu 2/13/14 | Wed 3/19/14
Finalize business process changes to support application or interface | 0% | 0 hrs | 25 days | Thu 2/13/14 | Wed 3/19/14
Procurement / Contracts | 0% | 0 hrs | 5 days | Wed 2/26/14 | Tue 3/4/14 | 384
Validate HW/SW/Mtc/Fees - No Cost to support contractual extension/mtc fees or SW | 0% | 0 hrs | 5 days | Wed 2/26/14 | Tue 3/4/14
Installation, Build & Testing | 0% | 0 hrs | 31 days | Mon 1/6/14 | Mon 2/17/14
Identify core infrastructure setup/changes & requirements | 0% | 0 hrs | 10 days | Mon 1/6/14 | Fri 1/17/14
Develop upgrade test plan and deployment plans | 0% | 0 hrs | 15 days | Mon 1/6/14 | Fri 1/24/14
Installation, Testing & Site Deployment | 0% | 0 hrs | 16 days | Mon 1/27/14 | Mon 2/17/14
Upgrade installation execution | 0% | 0 hrs | 5 days | Mon 1/27/14 | Fri 1/31/14 | 392
Execute application and/or interface testing | 0% | 0 hrs | 5 days | Mon 2/3/14 | Fri 2/7/14 | 394
Execute Weekly Checkpoint | 0% | 0 hrs | 5 days | Mon 2/3/14 | Fri 2/7/14 | 394
Execute User Acceptance Testing (UAT) for Process & Technology changes | 0% | 0 hrs | 10 days | Mon 2/3/14 | Fri 2/14/14 | 394
Gain UAT Signoff/Production Readiness | 0% | 0 hrs | 1 day | Fri 2/14/14 | Fri 2/14/14 | 397FF
Execute training to support application changes (Technical) | 0% | 0 hrs | 2 days | Mon 2/10/14 | Tue 2/11/14 | 395
Execute training to support process changes (Business Processes) | 0% | 0 hrs | 10 days | Mon 2/3/14 | Fri 2/14/14 | 394
Execute Production Cutover Activities/Vendor Migration | 0% | 0 hrs | 1 day | Fri 2/14/14 | Fri 2/14/14 | 398FF
Technology documentation to support post implementation mtc | 0% | 0 hrs | 5 days | Mon 2/3/14 | Fri 2/7/14 | 391394
Manange, Track and Remediate Defects | 0% | 0 hrs | 15 days | Mon 1/27/14 | Fri 2/14/14 | 401FF
Product Go Live | 0% | 0 hrs | 1 day | Mon 2/17/14 | Mon 2/17/14 | 401
Maestro | 0% | 0 hrs | 66 days | Mon 2/10/14 | Mon 5/12/14
Validate Readiness | 0% | 0 hrs | 30 days | Mon 2/10/14 | Fri 3/21/14
Revalidate vendor readiness/assumptions | 0% | 0 hrs | 10 days | Mon 2/10/14 | Fri 2/21/14
Ensure required change management plan / marketing plans in place to proactively drive change & adoption based upon process areas impacted & deliver per proposed planned schedule | 0% | 0 hrs | 10 days | Mon 2/24/14 | Fri 3/7/14 | 407
Identify risks, if any, if parallel use is required and system cannot support, availability/process areas impacted concerns | 0% | 0 hrs | 10 days | Mon 3/10/14 | Fri 3/21/14 | 408
Requirements & Design | 0% | 0 hrs | 25 days | Mon 3/24/14 | Fri 4/25/14 | 406
Validate/Define architectural design | 0% | 0 hrs | 9 days | Mon 3/24/14 | Thu 4/3/14
Validate technology requirements and system depenencies from vendor to facilitate upgrade | 0% | 0 hrs | 10 days | Mon 3/24/14 | Fri 4/4/14
Define environmental considerations for testing | 0% | 0 hrs | 5 days | Mon 3/24/14 | Fri 3/28/14
Finalize requirements and process dependencies across impacted stakeholders | 0% | 0 hrs | 25 days | Mon 3/24/14 | Fri 4/25/14
Finalize business process changes to support application or interface | 0% | 0 hrs | 25 days | Mon 3/24/14 | Fri 4/25/14
Procurement / Contracts | 0% | 0 hrs | 5 days | Fri 4/4/14 | Thu 4/10/14 | 411
Validate HW/SW/Mtc/Fees - No Cost to support contractual extension/mtc fees or SW | 0% | 0 hrs | 5 days | Fri 4/4/14 | Thu 4/10/14
Installation, Build & Testing | 0% | 0 hrs | 31 days | Mon 3/31/14 | Mon 5/12/14
Identify core infrastructure setup/changes & requirements | 0% | 0 hrs | 10 days | Mon 3/31/14 | Fri 4/11/14 | 413
Develop upgrade test plan and deployment plans | 0% | 0 hrs | 15 days | Mon 3/31/14 | Fri 4/18/14 | 413
Installation, Testing & Site Deployment | 0% | 0 hrs | 16 days | Mon 4/21/14 | Mon 5/12/14
Upgrade installation execution | 0% | 0 hrs | 5 days | Mon 4/21/14 | Fri 4/25/14 | 420
Execute application and/or interface testing | 0% | 0 hrs | 5 days | Mon 4/28/14 | Fri 5/2/14 | 422
Execute Weekly Checkpoint | 0% | 0 hrs | 5 days | Mon 4/28/14 | Fri 5/2/14 | 422
Execute User Acceptance Testing (UAT) for Process & Technology changes | 0% | 0 hrs | 10 days | Mon 4/28/14 | Fri 5/9/14 | 422
Gain UAT Signoff/Production Readiness | 0% | 0 hrs | 1 day | Fri 5/9/14 | Fri 5/9/14 | 425FF
Execute training to support application changes (Technical) | 0% | 0 hrs | 2 days | Mon 5/5/14 | Tue 5/6/14 | 423
Execute training to support process changes (Business Processes) | 0% | 0 hrs | 10 days | Mon 4/28/14 | Fri 5/9/14 | 422
Execute Production Cutover Activities/Vendor Migration | 0% | 0 hrs | 1 day | Fri 5/9/14 | Fri 5/9/14 | 426FF
Technology documentation to support post implementation mtc | 0% | 0 hrs | 5 days | Mon 4/28/14 | Fri 5/2/14 | 419422
Manange, Track and Remediate Defects | 0% | 0 hrs | 15 days | Mon 4/21/14 | Fri 5/9/14 | 429FF
Product Go Live | 0% | 0 hrs | 1 day | Mon 5/12/14 | Mon 5/12/14 | 429
Vendor/Payer Management/Communication Plan | 0% | 0 hrs | 254 days | Mon 10/14/13 | Mon 10/13/14
Vendor Communication Plan | 0% | 0 hrs | 254 days | Mon 10/14/13 | Mon 10/13/14
Monthly Monitoring of Vendor Readiness | 0% | 0 hrs | 254 days | Mon 10/14/13 | Mon 10/13/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 10/14/13 | Mon 10/14/13
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 11/11/13 | Mon 11/11/13
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 12/9/13 | Mon 12/9/13
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 1/13/14 | Mon 1/13/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 2/10/14 | Mon 2/10/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 3/10/14 | Mon 3/10/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 4/14/14 | Mon 4/14/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 5/12/14 | Mon 5/12/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 6/9/14 | Mon 6/9/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 7/14/14 | Mon 7/14/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 8/11/14 | Mon 8/11/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 9/8/14 | Mon 9/8/14
Vendor Readiness Monitoring | 0% | 0 hrs | 1 day | Mon 10/13/14 | Mon 10/13/14
Integration Testing for External Payor | 0% | 0 hrs | 232 days | Mon 1/6/14 | Tue 12/2/14
Test Environment Prepartion | 0% | 0 hrs | 53 days | Mon 1/6/14 | Wed 3/19/14
Validate Test Results from Integrated Testing | 0% | 0 hrs | 3 days | Mon 1/6/14 | Wed 1/8/14
Execute any required changes to establish External Intergrated Test Environment | 0% | 0 hrs | 7 days | Thu 1/9/14 | Fri 1/17/14 | 451
Establish the testing tools for External Payor Integration Testing | 0% | 0 hrs | 10 days | Mon 1/20/14 | Fri 1/31/14 | 452
Setup and configure testing defect management tool for External Payor Testing | 0% | 0 hrs | 3 days | Mon 2/3/14 | Wed 2/5/14 | 453
Create Test Data for Payor 1 | 0% | 0 hrs | 5 days | Thu 2/6/14 | Wed 2/12/14 | 454458
Execute peformance testing according to test case thresholds | 0% | 0 hrs | 5 days | Thu 2/13/14 | Wed 2/19/14 | 455
Execute data continuity testing to Clearinghouse | 0% | 0 hrs | 3 days | Thu 1/9/14 | Mon 1/13/14 | 451
Execute data continuity testing to Payor 1 | 0% | 0 hrs | 3 days | Tue 1/14/14 | Thu 1/16/14 | 457
Executes test cases/scripts as per test strategy for Payor 1 | 0% | 0 hrs | 10 days | Thu 2/13/14 | Wed 2/26/14 | 455458
Fix Class 1 defects identified and rework for Payor 1 | 0% | 0 hrs | 5 days | Thu 2/27/14 | Wed 3/5/14 | 459
IT work stream reviews documentation and results of integrated testing and coordinates with payor work stream for updates | 0% | 0 hrs | 5 days | Thu 3/6/14 | Wed 3/12/14 | 460
IT work stream coordinates update requirements, traceability and documents test results in coordination with payor work stream | 0% | 0 hrs | 5 days | Thu 3/13/14 | Wed 3/19/14 | 461
Execute Tier 1 Payor Testing (repeating for entire Tier) | 0% | 0 hrs | 95 days | Mon 2/3/14 | Mon 6/16/14
Create and validate test data for Tier 1 Vendor | 0% | 0 hrs | 20 days | Mon 2/3/14 | Fri 2/28/14
Execute data continuity testing to Tier 1 Payor | 0% | 0 hrs | 15 days | Mon 3/3/14 | Fri 3/21/14 | 464
Execute test cases/scripts as per test strategy for Tier 1 Payor | 0% | 0 hrs | 30 days | Mon 3/24/14 | Fri 5/2/14 | 465
Fix defects identified and rework for Tier 1 Payor | 0% | 0 hrs | 10 days | Mon 5/5/14 | Fri 5/16/14 | 466
IT work stream reviews documentation and results of integrated testing and coordinates with payor work stream for updates | 0% | 0 hrs | 10 days | Mon 5/19/14 | Mon 6/2/14 | 467
IT work stream coordinates update requirements, traceability and documents test results in coordination with payor work stream | 0% | 0 hrs | 10 days | Tue 6/3/14 | Mon 6/16/14 | 468
Execute Tier 2 Payor Testing (repeating for entire Tier) | 0% | 0 hrs | 95 days | Mon 5/19/14 | Wed 10/1/14
Create and validate test data for Tier 2 Vendor | 0% | 0 hrs | 20 days | Mon 5/19/14 | Mon 6/16/14 | 469FS-20 days
Execute data continuity testing to Tier 2 Payor | 0% | 0 hrs | 15 days | Tue 6/17/14 | Tue 7/8/14 | 471
Executes test cases/scripts as per test strategy for Tier 2 Payor | 0% | 0 hrs | 30 days | Wed 7/9/14 | Tue 8/19/14 | 472
Fix defects identified and rework for Tier 2 Payor | 0% | 0 hrs | 10 days | Wed 8/20/14 | Wed 9/3/14 | 473
IT work stream reviews documentation and results of integrated testing and coordinates with payor work stream for updates | 0% | 0 hrs | 10 days | Thu 9/4/14 | Wed 9/17/14 | 474
IT work stream coordinates update requirements, traceability and documents test results in coordination with payor work stream | 0% | 0 hrs | 10 days | Thu 9/18/14 | Wed 10/1/14 | 475
Execute Tier 3 Payor Testing (repeating for entire Tier) | 0% | 0 hrs | 72 days | Wed 8/20/14 | Tue 12/2/14
Create and validate test data for Tier 3 Vendor | 0% | 0 hrs | 20 days | Wed 8/20/14 | Wed 9/17/14 | 476FS-30 days
Execute data continuity testing to Tier 3 Payor | 0% | 0 hrs | 7 days | Thu 9/18/14 | Fri 9/26/14 | 478
Executes test cases/scripts as per test strategy for Tier 3 Payor | 0% | 0 hrs | 15 days | Mon 9/29/14 | Fri 10/17/14 | 479
Fix defects identified and rework for Tier 3 Payor | 0% | 0 hrs | 10 days | Mon 10/20/14 | Fri 10/31/14 | 480
IT work stream reviews documentation and results of integrated testing and coordinates with payor work stream for updates | 0% | 0 hrs | 10 days | Mon 11/3/14 | Fri 11/14/14 | 481
IT work stream coordinates update requirements, traceability and documents test results in coordination with payor work stream | 0% | 0 hrs | 10 days | Mon 11/17/14 | Tue 12/2/14 | 482
ICD-10 GO LIVE | 0% | 0 hrs | 1 day | Wed 10/1/14 | Wed 10/1/14
Phase 4 - Stabilize & Monitor | 0% | 2,064 hrs | 404 days | Tue 10/1/13 | Wed 5/6/15
Program Management Office | 0% | 2,064 hrs | 378 days | Tue 10/1/13 | Tue 3/31/15
Reporting, Issues and Risk Management | 0% | 0 hrs | 315 days | Tue 10/1/13 | Tue 12/30/14
Team Leads Status Reporting | 0% | 0 hrs | 315 days | Tue 10/1/13 | Tue 12/30/14
Program Budget & Analysis | 0% | 0 hrs | 315 days | Tue 10/1/13 | Tue 12/30/14
Issues & Risk Management | 0% | 0 hrs | 315 days | Tue 10/1/13 | Tue 12/30/14
Steering Committee Status Reporting | 0% | 0 hrs | 315 days | Tue 10/1/13 | Tue 12/30/14
Change Management & Communication (Program Related) | 0% | 0 hrs | 240 days | Mon 11/11/13 | Tue 10/21/14
Stakeholder Analysis | 0% | 0 hrs | 7 days | Mon 11/11/13 | Tue 11/19/13
Validate stakeholders | 0% | 0 hrs | 7 days | Mon 11/11/13 | Tue 11/19/13
Gather supporting materials by audience (logistics, counts….) | 0% | 0 hrs | 14 days | Mon 11/11/13 | Mon 12/2/13
Identify platforms/forum(s) for communication | 0% | 0 hrs | 7 days | Mon 11/11/13 | Tue 11/19/13
Define structure and team to support change management and awareness campaign | 0% | 0 hrs | 7 days | Wed 11/20/13 | Mon 12/2/13 | 496
Develop Messages and Plan | 0% | 0 hrs | 29 days | Tue 12/3/13 | Tue 1/14/14
Indicate communication developers and approvers | 0% | 0 hrs | 10 days | Tue 12/3/13 | Mon 12/16/13 | 497
Develop ICD-10 program brand & core messages | 0% | 0 hrs | 10 days | Tue 12/3/13 | Mon 12/16/13 | 497
Validate stakeholder analysis (groups and owners) | 0% | 0 hrs | 5 days | Tue 12/17/13 | Mon 12/23/13 | 500
Create ICD-10 case for change message | 0% | 0 hrs | 5 days | Tue 12/17/13 | Mon 12/23/13 | 499
Create ICD-10 elevator speech | 0% | 0 hrs | 14 days | Tue 12/24/13 | Tue 1/14/14 | 501
Develop initial set of ICD-10 FAQs or 'Top Ten' | 0% | 0 hrs | 14 days | Tue 12/24/13 | Tue 1/14/14
Assess/Implement communication needs by stakeholder group | 0% | 0 hrs | 26 days | Mon 1/6/14 | Mon 2/10/14
Align key messages to stakeholder groups | 0% | 0 hrs | 5 days | Mon 1/6/14 | Fri 1/10/14
Select communications vehicles | 0% | 0 hrs | 5 days | Mon 1/13/14 | Fri 1/17/14 | 506
Confirm assessment communication modalities for print/email/newsletter awareness | 0% | 0 hrs | 5 days | Mon 1/13/14 | Fri 1/17/14 | 506
Develop communications plan by stakeholder group | 0% | 0 hrs | 21 days | Mon 1/13/14 | Mon 2/10/14 | 506
Execute Communication Plan | 0% | 0 hrs | 178 days | Tue 2/11/14 | Tue 10/21/14
Distribute communications materials (per plan) | 0% | 0 hrs | 14 days | Tue 2/11/14 | Fri 2/28/14 | 509
Implement communications activities and events | 0% | 0 hrs | 14 days | Mon 3/3/14 | Thu 3/20/14 | 511
Manage status of communication work products (weekly) | 0% | 0 hrs | 150 days | Fri 3/21/14 | Tue 10/21/14 | 512
Understand and align physician documentation practices | 0% | 0 hrs | 75 days | Tue 1/28/14 | Mon 5/12/14
Review by-laws/ medical staff rules/regs | 0% | 0 hrs | 5 days | Tue 1/28/14 | Mon 2/3/14
Determine best practice for physician documentation | 0% | 0 hrs | 5 days | Tue 2/4/14 | Mon 2/10/14 | 515
Interview physicians | 0% | 0 hrs | 20 days | Tue 2/11/14 | Mon 3/10/14 | 516
Clarify physician documentation expectations | 0% | 0 hrs | 20 days | Tue 3/11/14 | Mon 4/7/14 | 517
Communicate documentation expectations to all physicians | 0% | 0 hrs | 15 days | Tue 4/8/14 | Mon 4/28/14 | 518
Document documentation expectations (update medical staff rules/regs or by-laws) | 0% | 0 hrs | 10 days | Tue 4/29/14 | Mon 5/12/14 | 519
Weekly review of high risk/problem prone cases | 0% | 0 hrs | 90 days | Tue 5/27/14 | Wed 10/1/14
Schedule weekly review | 0% | 0 hrs | 90 days | Tue 5/27/14 | Wed 10/1/14
Complete report for weekly distribution | 0% | 0 hrs | 90 days | Tue 5/27/14 | Wed 10/1/14
Deliver report to secondary resource for quality review | 0% | 0 hrs | 90 days | Tue 5/27/14 | Wed 10/1/14
Finalize report | 0% | 0 hrs | 90 days | Tue 5/27/14 | Wed 10/1/14
Publish findings | 0% | 0 hrs | 90 days | Tue 5/27/14 | Wed 10/1/14
Deliver and Monitor Change | 0% | 0 hrs | 170 days | Tue 2/11/14 | Thu 10/9/14
Provide remediation with documentation outliers | 0% | 0 hrs | 170 days | Tue 2/11/14 | Thu 10/9/14
Update change management strategy and plan, as needed (monthly) | 0% | 0 hrs | 170 days | Tue 2/11/14 | Thu 10/9/14
Post Go-Live Operational Support | 0% | 2,064 hrs | 128 days | Thu 9/25/14 | Tue 3/31/15
Post Go-Live Documentation Assessment | 0% | 0 hrs | 30 days | Thu 9/25/14 | Wed 11/5/14 | 484FS-5 days
Productivity Loss After Go-Live | 0% | 2,064 hrs | 123 days | Thu 10/2/14 | Tue 3/31/15
Post Go-Live Coding Audit | 0% | 0 hrs | 25 days | Thu 10/2/14 | Wed 11/5/14 | 484
Project Closure | 0% | 0 hrs | 36 days | Thu 11/6/14 | Wed 12/31/14
Finalize Document Repositories | 0% | 0 hrs | 36 days | Thu 11/6/14 | Wed 12/31/14
Soft Copy Documents | 0% | 0 hrs | 26 days | Thu 11/6/14 | Mon 12/15/14
Review all Directories & Files | 0% | 0 hrs | 10 days | Thu 11/6/14 | Wed 11/19/14 | 533
Develop Consolidated Directory | 0% | 0 hrs | 5 days | Thu 11/20/14 | Wed 11/26/14 | 537
File Documents in Consolidated Directory | 0% | 0 hrs | 10 days | Mon 12/1/14 | Fri 12/12/14 | 538
Reconcile to Delivery site, as needed | 0% | 0 hrs | 1 day | Mon 12/15/14 | Mon 12/15/14 | 539
Hard Copy Documents | 0% | 0 hrs | 25 days | Thu 11/20/14 | Tue 12/30/14
Assess need for hardcopy documents | 0% | 0 hrs | 10 days | Thu 11/20/14 | Fri 12/5/14 | 537
Determine hardcopy document retention requirements | 0% | 0 hrs | 5 days | Mon 12/8/14 | Fri 12/12/14 | 542
Arrange for support for hardcopy document retention | 0% | 0 hrs | 5 days | Mon 12/15/14 | Fri 12/19/14 | 543
Archive hardcopy documents | 0% | 0 hrs | 5 days | Mon 12/22/14 | Tue 12/30/14 | 544
Finalize Document Repository | 0% | 0 hrs | 1 day | Wed 12/31/14 | Wed 12/31/14 | 536541
Lessons Learned | 0% | 0 hrs | 20 days | Mon 11/24/14 | Tue 12/23/14
Gather Lessons Learned from Teams | 0% | 0 hrs | 10 days | Mon 11/24/14 | Tue 12/9/14
Consolidate Lessons Learned Document | 0% | 0 hrs | 4 days | Wed 12/10/14 | Mon 12/15/14 | 548
Schedule Lesson Learned Review with Team | 0% | 0 hrs | 2 days | Tue 12/16/14 | Wed 12/17/14 | 549
Execute Lessons Learned session | 0% | 0 hrs | 1 day | Thu 12/18/14 | Thu 12/18/14 | 550
Complete/Incorporate Review of Lessons Learned from Team | 0% | 0 hrs | 1 day | Fri 12/19/14 | Fri 12/19/14 | 551
Compile Lessons Learned consolidated document | 0% | 0 hrs | 2 days | Mon 12/22/14 | Tue 12/23/14 | 552
Ownership Transition for Trailing Issues (TI) | 0% | 0 hrs | 25 days | Fri 11/7/14 | Mon 12/15/14
Define Ultimate Owners & Key Players | 0% | 0 hrs | 5 days | Fri 11/7/14 | Thu 11/13/14 | 548FS-21 days
Engage Key Players in development of Ownership Transition Plan | 0% | 0 hrs | 10 days | Fri 11/14/14 | Mon 12/1/14 | 555
Trailing Issues (TI) Ownership Transition | 0% | 0 hrs | 5 days | Tue 12/2/14 | Mon 12/8/14 | 556
Review work plan & develop baseline TI list | 0% | 0 hrs | 5 days | Tue 12/9/14 | Mon 12/15/14 | 557
Provide TI list and instructions to Transition Lead (TL) | 0% | 0 hrs | 6 days | Tue 12/16/14 | Tue 12/23/14
Assign long term ownership to owners | 0% | 0 hrs | 5 days | Tue 12/16/14 | Mon 12/22/14 | 558
Report Ownership Transition to Exec | 0% | 0 hrs | 1 day | Tue 12/23/14 | Tue 12/23/14 | 560
Operations | 0% | 0 hrs | 51 days | Mon 11/3/14 | Tue 1/20/15
Post ICD-10 Implementation Process (Coding and Documentation Review after implementation) | 0% | 0 hrs | 51 days | Mon 11/3/14 | Tue 1/20/15
Determine when the coding documentation review will occur | 0% | 0 hrs | 5 days | Mon 11/3/14 | Fri 11/7/14
Schedule the Documentation Review | 0% | 0 hrs | 5 days | Mon 11/10/14 | Fri 11/14/14 | 564
Identify the medical records to review | 0% | 0 hrs | 5 days | Mon 11/17/14 | Fri 11/21/14 | 565
Perform the documentation review | 0% | 0 hrs | 15 days | Mon 11/24/14 | Tue 12/16/14 | 566
Identify the educational opportunities from the medical records | 0% | 0 hrs | 15 days | Wed 12/17/14 | Mon 1/12/15 | 567
Conduct education with coders and/or providers based on the documentation review | 0% | 0 hrs | 3 days | Tue 1/13/15 | Thu 1/15/15 | 568
Provide a comprehensive final report that contains recommendations and areas of improvement based on the findings | 0% | 0 hrs | 3 days | Fri 1/16/15 | Tue 1/20/15 | 569
Finance | 0% | 0 hrs | 150 days | Wed 10/1/14 | Wed 5/6/15
Post Go Live Claims/Cash Flow Management | 0% | 0 hrs | 150 days | Wed 10/1/14 | Wed 5/6/15
Ongoing monitoring of ICD-10 dashboards - claims | 0% | 0 hrs | 150 days | Wed 10/1/14 | Wed 5/6/15
Identify and remediate root cause of findings above | 0% | 0 hrs | 150 days | Wed 10/1/14 | Wed 5/6/15
Information Technology (IT) | 0% | 0 hrs | 60 days | Wed 10/1/14 | Mon 12/29/14
All Systems, Payers and Vendors | 0% | 0 hrs | 60 days | Wed 10/1/14 | Mon 12/29/14
Execute/Support Post Go Live (as needed) | 0% | 0 hrs | 60 days | Wed 10/1/14 | Mon 12/29/14
Follow-up training and change management within IT | 0% | 0 hrs | 60 days | Wed 10/1/14 | Mon 12/29/14